## Slide 1: Qiskit Advocate Mentorship Program
Eraraya Ricardo Muten
Engineering Physics Undergraduate, Quantum Tech. Lab Bandung Institute of Technology
Mentor: Anna Phan Research Scientist at IBM
Project: #43 QML Qiskit Implementations

## Slide 2: Project Description
Implement the “Data re-uploading for a universal quantum classifier” paper by Pérez-Salinas et al.[1] in Qiskit to classify PCA-reduced MNIST Dataset[2]. Write a blog post showing the code and explaining the difference between Qiskit implementation and other platform (PennyLane) implementation.
Implement “Quantum Graph Neural Networks” paper by Verdon et al.[3] in Qiskit. The notebook will be written as a Qiskit Textbook entry for the section 4.2.

## Slide 3: Progress
The final notebook for project number 1 is finished. We obtained similar training and testing accuracy compared to the PennyLane implementation. For binary classification (0 vs 1) we obtained: The difference comes from the different optimizers, hyperparameters (e.g., max iter: 10 Adam iteration with 13 batches/iteration for PennyLane and 1000 COBYLA iteration for Qiskit) and backends used.
The notebook can be accessed here (GitHub repo): http://bit.ly/Qiskit-Mentorship

## Slide 4: Next Target
Write the blog post for project number 1.
Start to read the reference [3] paper comprehensively.
Write a temporary notebook for project number 2.

## Slide 5: References
[1] Pérez-Salinas A, Cervera-Lierta A, Gil-Fuster E, Latorre JI. Data reuploading for a universal quantum classifier. Quantum 2020;4:226. https://doi.org/10.22331/q-2020-02-06-226.
[2] LeCun Y, Cortes C. MNIST handwritten digit database 2010.
[3] Verdon G, McCourt T, Luzhnica E, Singh V, Leichenauer S, Hidary J. Quantum Graph Neural Networks. ArXiv 2019.

## Slide 6: Data Re-uploading Classifier (DRC)
An example of 1-qubit DRC circuit.
1-layer DRC circuit.
Multi-layer DRC circuit.